## Sheet1
SEATTLE CENTRAL COLLEGE
BUDGET DEVELOPMENT SCHEDULE
FY2016-17
DATE | ACTIVITY
Jan. 25 - Feb 16, 2016 | College Council recommend budget planning principles
Feb 16 - Feb. 29, 2016 | Cabinet review and approve budget planning principles
Feb. 29 - March 15, 2016 | Departments to review current year's budget
Feb 16 - March 8, 2016 | Work group to complete revisions to the Budget Request form
March 7 - 23 2016 | 2016 - 2020 Strategic Plan drafted
March 23 - April 8th, 2016 | Instructional unit to prepare AH/AF/AG requests for 2016-17
March 24 - April 15, 2016 | Units (Instructional, SS, & Admin) to prepare one-time budget proposals for 2016-17 Department Strategic Action Plans due to respective VPs
April 16 - April 29, 2016 | VP's prioritize budget requests with unit leaders
May 2, 2016 | Campus Budget Planning Forum
May 4, 2016 | SVI Budget Planning Forum
May 2 - May 12, 2016 | College Council Budget Work Group prioritize budget requests
May 13, 2016 | Executive Team to review and prioritize units' budget proposals | Schedule ad hoc meeting
May 17, 2016 | President's Cabinet advise Executive Team onpriorities for new budget requests.
May 25 - 26, 2016 | VPAS to present one-time requests to College Council | Check college council schedule and adjust
May 25 - 26, 2017 | College Council to provide feedback on budget proposals to VPAS
May 27, 2016 | VPAS draft preliminary budget 2016-17 (Operating & Local)
May 31, 2016 | Executive Team to review preliminary budget
June 1, 2016 | SVI Budget Presentation (tentatively scheduled)
June 1, 2016 | VPAS to present budget to College Council
June 6, 2016 | Central Budget Presentation (tentatively scheduled)
June 7, 2016 | WT Budget Presentation (tentatively scheduled)