## Sheet1
seattleCollege ctcLink Implementation Risk Matrix
Likelihood | 5 |  |  |  | B | C
| 4 |  | H,I | D,G |  | E
| 3 |  |  | A | F,J,K
2
1
|  | 1 | 2 | 3 | 4 | 5
Consequence
ü=Mitigation in Place
[8 empty] | Risk Description | Mitigation
[7 empty] | A | FirstWve Colleges may be delayed and that would impact Seattles College schedule
[7 empty] | B | Insufficient level of staffing for SMEs (Backfilling, O.T., etc) will not provide required resources for implementation
[7 empty] | C | Insufficient Budget would limit SME resources, travel to firstLink colleges, travel to training, facilities requirements
[7 empty] | D | Lack of a suitable control room and equipment could result in inability to complete UAT and other key project deliverables
[7 empty] | E | Other College Improvement Initiatives (Budget reductions, new BAS programs, etc.) competing for SME time could result in taking key SMEs away from ctcLink Implementation
[7 empty] | F | Insufficient information on data cleansing requirements could lead to last minute failures during data conversion
[7 empty] | G | Alignment across all three campuses might interfere with ctcLink implementation by taking resources away functional areas.
[7 empty] | H | Not including the right people in Business Process Analysis, Training and User Acceptance Testing could result in people not familiar with PeopleSoft at go live
[7 empty] | I | We may spend time learning current version of PeopleSoft and when we go live there may be a new version
[7 empty] | J | Distributing Financial Aid on July 1 (New Financial Aid Year) could be impacted with a ctcLink go live date in May
[7 empty] | K | There may be inadequate SB resources available for configuration, UAT and Training, which could impact Seattle Colleges ability to meet schedule
1. Perform bottom up estimate
2. Submit estimate to College ctcLink Executive Sponsor
1. Meet with firstLink colleges to define staffing requirements
2. Determine budget requirements
3. Hire 2 Analysts to perform data cleansing, validation, configuration, acceptance testing, and design ODS
4. Submit staffing and budget requirements to VPs
1. Meet with firstLink and Wave 1 colleges to define control room requirements 2. Document control room requirements and submit to VPs 3. Look for open space
1. Engage Faculty 2. Engage Students 3. Communicate project status and look for individuals ready to participate
1. Monitor SB Project Schedule and adjust Seattle
College schedule as needed
1. Use material currently available (UPKs, PeopleBook & BPA sessions) to become familiar with PeopleSoft
2. Address College and SB resources in Training Plan
1. Before training begins, spend time on familiarizing, but not detailed learning/training
2. Keep SCC schedule current to SB
1. Check with FirstLink schools to get best practice for organizaing alignment across all three campuses.
2. Adjust resources as required
1. Vice Presidents/HR Director need to keep SMEs focused on ctcLink
2. Vice Presidents/HR Director review monthly project status with their SMEs
3. Present project status to VPs/HR Director and encourage them to support SMEs
1. Make sure all Financial Aid employees are extensively trained and ready to distribute Financial Aid on go live date.
2. Ask FirstLink and Wave 1 school(s) for advice
1. Contact SBctc and request specific list of data cleansing requirements
2. Check with firstLink school(s) to determine data cleansing requirements
1. Contact SBctc and request specific list of data cleansing requirements
2. Check with firstLink school(s) to determine data cleansing requirements