## Sheet1
| Pillar Lead | HR & Financial Analysts | Student Services & Financial Aid Analysts | Functional SME | Program Manager | SW Security Manger | Technical Coordinator | Supplemental Systems Analysis Team | Executive Sponsor | VPs
Develop and Maintain Project Plan | S |  |  | S | R |  |  |  | A | S
Participate in Project Management Meetings | S | S | S | S | R | S | S |  | S | A
Define Post-PeopleSoft ODS Database Requirements | S | R | R |  | A
Design and Develop ODS Database | S | R | R |  | A
Perform Legacy Data Cleansing | S | R | R |  | A
Perform Conversion Data Validation | S | R | R | S | A
Perform User Acceptance Testing | S | R | R | S | A
Analyze required/available reports and develop as needed | S | R | R | S | A
Develop Configuration values | S | R | R | S | A
Inventory Shadow Systems and develop recommendations | S | S | S |  | A |  |  | R
Oversee Change Management efforts | S | S | S | S | R |  |  |  | A | S
Disseminate ctcLink communications, maintain surveys | S | S | S | S | R |  |  |  | A | S
Point of Contact with SB ctcLink Team for Wave 2 Implementation |  |  |  |  | R |  |  |  | A
Schedule Pillar Business Process Analysis and Improvement workshops | R |  |  | S | S |  |  |  |  | A
Facilitate Business Process Analysis and Improvement Workshops |  |  |  |  | R |  |  |  | A
Develop Pillar training plan and manage training schedule and facilities | R |  |  |  | A
Practice in "Sandbox" prior to training | R | S | S | S | S |  |  |  |  | A
Attain PeopleSoft "Super User" status | R | S | S |  | S |  |  |  |  | A
Resolve college specific technical issues | [6 empty] | R |  | A
Manage College Pre and Post Go-Live System Security (PeopleSoft Roles) | [5 empty] | R |  |  | A
Coordinate Pillar Pre and Post Go-Live Security (PeopleSoft Roles) | R |  |  | S | [5 empty] | A
Manage PeopleSoft Configuration-Change Board Member | R |  |  |  | S |  |  |  |  | A
Project Monitor & Control, Monthly Metrics | S | S | S | S | R |  |  |  | A | S
Resolve college specific issues, monitor overall status | [8 empty] | R